### PUL GLOBAL PARTNERS

# Website Redesign and Digital Presence Project Management Plan

Agile delivery framework for design, content, development, approval, deployment, and continuous governance

Prepared for executive approval and implementation planning

Version 1.1  |  Plan owner: PUL Global Partners  |  Delivery window: review build in progress

# Executive Decision

Recommendation. Build a separate, static-first Next.js App Router website using TypeScript. Preserve the approved PUL page framework and design direction. Manage occasional Insights articles as local MDX files that are versioned with the site and rendered into static article pages. Start without a database, hosted CMS, or server-side content service. Keep the current WordPress website and deployed Vercel review site unchanged; the new application is for local review only until separately accepted and explicitly authorized for release.

This approach matches the user's preference for code-first changes through ongoing collaboration and the expected low volume of routine edits with occasional Insights publishing. MDX avoids the operational overhead of a database or CMS while keeping articles structured and maintainable. The accepted tradeoff is that routine content edits require a developer or agent. Reassess a CMS only if staff need frequent self-service publishing or formal editorial approvals. Next.js does require a supported build and hosting workflow, so production compatibility and release controls must be reviewed separately; this approval does not change the live site.

## Approval Requested

Approve the separate Next.js and TypeScript review build, with MDX for occasional Insights and no database or CMS at outset.

Approve the project governance model, delivery stages, review gates, and change-control process.

Approve development of coordinated AI-generated conceptual imagery with clear safeguards against misrepresentation.

Approve preservation of the existing page framework while enriching content, visuals, proof, and procurement readiness.

Authorize implementation only after this plan and its first prioritized backlog are reviewed.

## Project Outcomes

| Outcome | Definition of success |
| --- | --- |
| Professional market position | The site communicates PUL as a U.S.-registered implementation partner across consulting, capacity building, technology and AI, and mission support. |
| Procurement readiness | UEI, CAGE, NAICS, capability statement, buyer fit, competencies, and institutional-heritage disclosures are easy to find and accurate. |
| Design advancement | The experience is materially stronger than the current site while remaining recognizably PUL and preserving familiar page organization. |
| Evidence-led credibility | Documented projects, metrics, and approved references are presented clearly without overstating current-entity experience. |
| Operational ownership | PUL staff can update ordinary content without developer intervention, and technical changes follow repository and release controls. |
| Deployment readiness | The final package is tested, documented, backed up, reversible, and ready for one.com deployment by PUL or its IT Manager. |

# 1 Project Charter

## 1.1 Purpose

The project will improve PUL Global Partners' digital presence through a controlled redesign and content enrichment program. The work preserves the approved page concept, strengthens visual and editorial quality, adds approved capability and past-performance content, and introduces appropriate imagery. A separate Next.js review build will be prepared without changing the live website; any production package and hosting decision require a later approval gate.

## 1.2 Business Need

The current website presents PUL primarily as a Virginia government-contracting consultant. The approved Company Profile and Capability Statement establish a broader and more credible market position: a U.S.-registered partner for federal contracting, overseas mission support, management consulting, technology and responsible AI enablement, capacity building, logistics, and international implementation.

## 1.3 Objectives

Align every public page with the final Company Profile and Capability Statement.

Increase executive, federal-buyer, prime-contractor, mission, and partner confidence.

Preserve the existing Home, Solutions, About, Projects, Insights, Careers, and Contact page framework while improving their composition and purpose.

Add a dedicated capability statement experience and enrich project or past-performance presentation.

Create a coherent image system combining approved real assets and clearly conceptual AI-generated visuals.

Improve mobile responsiveness, accessibility, loading performance, SEO, forms, analytics, and maintainability.

Deliver deployment instructions, backups, acceptance evidence, and a current repository record.

## 1.4 Success Measures

| Measure | Target | Verification |
| --- | --- | --- |
| Executive acceptance | All priority pages and messaging approved | Signed acceptance checklist or written approval |
| Content alignment | No unresolved conflict with approved source documents | Page-by-page content matrix review |
| Accessibility | WCAG 2.2 AA checks passed for priority templates | Automated scan plus keyboard and visual review |
| Performance | Mobile Lighthouse target of 85+ where hosting and third-party scripts permit | Prelaunch test on representative pages |
| Responsive quality | No clipping, overflow, overlap, or unusable controls | 320, 390, 768, 1024, and 1440 px review |
| Conversion readiness | Primary actions, forms, downloads, and inquiry routes function | End-to-end acceptance tests |
| Governance | Repository, status, decisions, backlog, change log, and deployment records current | End-of-session checklist |

# 2 Scope Management

## 2.1 In Scope

Discovery confirmation, page inventory, design system, content architecture, responsive visual design, a separate Next.js application, testing, local review, and future deployment preparation subject to a separate approval.

Enrichment of Home, Solutions, About, Projects, Insights, Careers, Contact, Privacy, header, footer, navigation, and global calls to action.

New capability statement page or section, downloadable document module, procurement credential strip, buyer pathways, delivery model, and institutional-heritage disclosures.

Past-performance enrichment within the existing Projects framework or a separately approved Past Performance page.

Eight to twelve coordinated AI-generated conceptual images, subject to review and labeling rules, plus optimized WebP or AVIF derivatives.

SEO titles, descriptions, headings, internal links, redirects where approved, organization schema, breadcrumbs, image alternative text, and social sharing metadata.

Form usability, email delivery checks, spam protection, consent language, analytics events, and download tracking.

Deployment runbook, rollback plan, content editor guide, and post-launch verification.

## 2.2 Out of Scope Unless Approved Through Change Control

A database, hosted CMS, authenticated portal, CRM replacement, e-commerce platform, multilingual translation program, or custom procurement system in the initial build. Production migration or hosting changes are also excluded until reviewed and approved separately.

Creation of unverified client testimonials, contract outcomes, certifications, government affiliations, staff biographies, or project photographs.

Major corporate rebranding, logo replacement, legal advice, SAM registration changes, cybersecurity certification, or paid advertising campaigns.

Removal or renaming of existing pages beyond approved redirects and navigation improvements.

Ongoing hosting administration after the agreed stabilization period.

## 2.3 Design Principles

| Principle | Application |
| --- | --- |
| Recognizably PUL | Preserve the logo, approved brand colors, existing page intent, and established corporate material while improving typography, spacing, imagery, and consistency. |
| Clear like QuantuTech | Use strong hierarchy, concise propositions, visible proof, logical narrative, and focused calls to action without copying its boutique visual identity. |
| Credible like Tetra Tech | Organize capabilities and project evidence with institutional clarity, buyer relevance, and implementation depth. |
| Evidence before decoration | Give priority to verified credentials, competencies, project scope, metrics, and delivery approach. |
| Visual restraint | Use one strong visual per major section; avoid repetitive decorative cards, excessive gradients, or imagery that implies unperformed work. |
| Accessible and fast | Design for keyboard users, readable contrast, responsive text, optimized assets, and minimal script overhead. |

# 3 Technology and Architecture

## 3.1 Recommended Stack

| Layer | Technology | Reason |
| --- | --- | --- |
| Framework | Next.js App Router | Provides reusable routes and components with static generation for the corporate site. |
| Language | TypeScript | Adds typed content and component contracts and aligns with established family-site codebases. |
| Content | Local MDX files for Insights; structured page content in source | Supports occasional article publishing without a database or CMS; changes remain reviewable in version control. |
| Rendering | Static-first generation | Serves prebuilt pages efficiently and avoids a runtime backend where the content does not require one. |
| Front end | Semantic HTML, modern CSS, optimized images, minimal client JavaScript | Supports accessibility, performance, responsive layouts, and maintainability. |
| Development | Separate `next-app/` application; existing prototype retained | Enables review without disturbing the deployed website or reference implementation. |
| Build output | Next.js static export | Emits a prebuilt site that can be reviewed locally and deployed to a static host such as one.com or Vercel after a separate release approval. |
| Deployment | Not authorized for production | No push, Vercel project change, DNS change, or deployment until acceptance, IT review, and explicit release authorization. |

## 3.2 Why This Architecture and Its Tradeoffs

Next.js and TypeScript provide a structured, reusable codebase that matches the user's other websites and supports this conversation-led update workflow. Locally authored MDX is proportionate to occasional article publishing and avoids introducing database and CMS operations before they are needed. Those tradeoffs are accepted for the review build. A static export can be hosted on a compatible web server or Vercel without a Node.js runtime, but the exact production host, domain settings, integrations, and release controls still require IT review and separate approval.

## 3.3 Performance Guardrails

No new plugin without documented need, owner, update policy, and performance review.

No page-critical animation library; motion must be subtle, optional, and reduced-motion aware.

Use responsive AVIF/WebP images with width and height attributes; lazy-load below-fold media.

Use global CSS tokens and reusable templates instead of repeated widget-level styling.

Load fonts locally where licensing permits and limit font families and weights.

Defer noncritical scripts and review analytics or marketing tags before launch.

Avoid sliders for primary messaging or proof.

# 4 Information Architecture and Page Plan

The current page framework will remain recognizable. Enrichment will happen through new sections, clearer sequencing, better visual evidence, and selected new destinations rather than an unnecessary restructuring of the entire site.

| Page | Planned enrichment | Primary approval |
| --- | --- | --- |
| Home | Enterprise proposition, credentials, four platforms, buyer pathways, evidence, delivery model, insights, final CTA | Executive positioning and claims |
| Solutions | Reorganized four-platform capabilities, service details, buyer fit, proof references, capability download | Service owners |
| About | Entity story, 2010 institutional heritage, operating model, leadership, differentiators, disclosure | Executive and legal/entity review |
| Projects | Documented engagements, capability tags, scope summaries, dates, outcomes where verified, heritage disclosure | Contracts and evidence owner |
| Insights | Capability-aligned categories, updated article framing, author and review dates, contextual CTAs | Content owner |
| Careers | Talent and partner network, role families, secure inquiry or deliberate temporary state | HR or executive owner |
| Contact | Direct contact details, inquiry routing, concise form, capability download, response expectation | Operations owner |
| Privacy | Actual form, analytics, cookie, retention, and contact practices | Qualified legal review |
| New capability destination | HTML capabilities overview, SAM data, NAICS, competencies, buyer fit, downloadable PDF | Executive and contracting review |

# 5 Visual Design and Image Strategy

## 5.1 Visual Direction

The design will combine QuantuTech’s clarity and conversion flow with Tetra Tech’s institutional organization and project storytelling. PUL’s approved navy, clear blue, white, light neutral, and restrained gold palette will remain the governing brand system. Typography will be authoritative and readable, with a professional sans-serif foundation and optional restrained editorial accent only where it supports hierarchy.

## 5.2 AI Generated Image Program

| Image theme | Likely placement | Control |
| --- | --- | --- |
| Global strategy and partnership | Home hero | Conceptual; avoid flags, seals, uniforms, or identifiable officials |
| Program and project delivery | Management consulting section | Show coordinated work, not a claimed PUL project |
| Capacity building and training | Solutions and About | Represent diverse professional participants respectfully |
| Responsible AI and digital workflows | Technology section | Show credible human-centered use, not science-fiction imagery |
| Networks and IT operations | Technology capability | Use technically plausible environments |
| Procurement and logistics | Mission support section | Show organized supply movement without branded government assets |
| Overseas mission coordination | Home or mission-support section | Conceptual operations setting with no implied embassy affiliation |
| Language and stakeholder engagement | Capacity-building section | Human review and facilitated communication |
| Economic growth and SME support | Projects or capability content | Market-facing enterprise support without invented beneficiaries |
| Events and hospitality | Mission support | Professional coordination without portraying an actual named engagement |

## 5.3 Image Governance

AI-generated images are illustrative and must never be used as proof of completed work.

No fabricated client, government, military, embassy, USAID, contractor, certification, uniform, badge, seal, or document branding.

No depiction of actual PUL personnel without consent and an approved reference image workflow.

Past-performance pages use real approved assets, neutral diagrams, maps, document excerpts, or clearly labeled illustrative imagery.

Each approved image receives an asset ID, prompt record, generation date, rights note, alt text, page assignment, crop variants, and executive approval status.

Human review must check anatomical errors, cultural sensitivity, technical plausibility, misleading details, embedded text, and visual consistency.

Final assets are exported in desktop and mobile-safe compositions and optimized before integration.

# 6 Agile Delivery Model

## 6.1 Method

The project will use a lightweight Scrum and Kanban hybrid. Work will be organized into short, outcome-based sprints with a prioritized backlog, visible acceptance criteria, scheduled review points, and controlled work in progress. Executive approval gates will protect strategy and claims; daily implementation decisions will remain within the approved design system and backlog.

## 6.2 Roles and Responsibilities

| Role | Accountability |
| --- | --- |
| Executive Sponsor | Approves strategy, scope, budget assumptions, corporate claims, launch, and major changes. |
| Product Owner | Prioritizes backlog, consolidates stakeholder feedback, accepts completed stories, and resolves business questions. |
| Delivery Lead and Agile Project Manager | Maintains plan, backlog, risks, decisions, status, sprint goals, dependencies, and change control. |
| Design and Development Lead | Produces UX, visual system, components, WordPress implementation, performance work, and technical documentation. |
| Content Owner | Approves copy, sources, metadata, institutional-heritage language, and editorial consistency. |
| Evidence and Compliance Reviewer | Validates legal name, identifiers, NAICS, metrics, client references, logos, outcomes, and project attribution. |
| IT Manager | Provides production access, hosting constraints, backup support, security review, deployment participation, and post-launch ownership. |
| Quality Reviewer | Executes responsive, accessibility, browser, form, content, link, performance, and regression tests. |

## 6.3 Definition of Ready

Business objective and page destination are clear.

Source content and evidence are identified.

Required assets and approvals are available or explicitly marked as assumptions.

Acceptance criteria and responsive expectations are written.

Dependencies, risks, and data or privacy implications are recorded.

The Product Owner has assigned priority.

## 6.4 Definition of Done

Acceptance criteria are met and demonstrated.

Desktop, tablet, and mobile states are complete.

Content, claims, links, accessibility, performance, and metadata checks pass.

Reusable code or template changes are committed with clear messages.

Relevant backlog, status, decisions, change log, test evidence, and documentation are updated.

The Product Owner accepts the item or records specific corrective work.

# 7 Work Breakdown and Schedule

| Phase | Duration | Principal outputs | Approval gate |
| --- | --- | --- | --- |
| 0 Authorization and setup | 1 to 2 days | Approved plan, repository, backlog, roles, source inventory, access checklist | Plan approval |
| 1 Discovery confirmation | 2 to 3 days | Technical inventory, page/content map, analytics questions, evidence register, constraints | Discovery signoff |
| 2 Design system and Home concept | 5 to 7 days | Tokens, typography, imagery direction, header/footer, homepage responsive concept | Visual direction approval |
| 3 Core page design | 5 to 7 days | Solutions, About, Projects, capability destination, Contact templates | Page design approval |
| 4 Content and asset production | Runs in parallel, 5 to 8 days | Final copy, metadata, AI imagery, optimized assets, claim register | Content and image approval |
| 5 Local Next.js build | 7 to 10 days | Next.js application, MDX content model, reusable pages, responsive implementation | Local feature review |
| 6 QA and refinement | 3 to 5 days | Accessibility, responsive, browser, content, form, link, SEO, performance test results | Release candidate approval |
| 7 Deployment preparation | 1 to 2 days | Backup, runbook, rollback plan, production checklist, handoff guide | Launch authorization |
| 8 Deployment and stabilization | 1 to 2 days plus monitoring | Production release, smoke tests, issue log, final archive | Project acceptance |

Estimated calendar duration. The separate local review build proceeds in short increments. Production release timing is not estimated until the hosting model, integrations, IT constraints, and executive approval are confirmed.

# 8 Initial Product Backlog

| Priority | Epic | Representative stories |
| --- | --- | --- |
| P0 | Governance and evidence | Confirm legal entity data; create claim register; identify approved logos, photographs, metrics, testimonials, and project evidence. |
| P0 | Design foundation | Define brand tokens, typography, spacing, grid, buttons, forms, navigation, card usage, imagery rules, and accessibility states. |
| P0 | Home | Create approved responsive Home concept that establishes positioning, credentials, capabilities, buyer fit, evidence, and CTA. |
| P0 | Capabilities | Build four-platform capability presentation and downloadable capability statement experience. |
| P0 | Projects | Replace generic duplication with documented institutional experience and transparent attribution. |
| P1 | About | Present the entity story, heritage, operating model, leadership, differentiators, and disclosure. |
| P1 | Contact | Create qualified inquiry flow, contact details, form validation, consent, response state, and tracking. |
| P1 | AI imagery | Generate, review, approve, optimize, document, and integrate the coordinated image set. |
| P1 | Careers | Publish a functional talent and partner-network experience or approve a deliberate temporary state. |
| P1 | Insights | Align categories, refresh stale content presentation, and define governance for new articles. |
| P1 | Quality and SEO | Complete responsive, accessibility, performance, metadata, schema, internal-link, redirect, and browser checks. |
| P2 | Post-launch optimization | Review analytics, search performance, form quality, content cadence, and improvement backlog. |

# 9 Review and Approval Plan

| Gate | Review package | Approver | Decision |
| --- | --- | --- | --- |
| G1 Plan | This project plan, technology decision, scope, governance, schedule | Executive Sponsor | Approve, revise, or hold |
| G2 Direction | Home desktop/mobile concept, design tokens, image style samples | Executive Sponsor and Product Owner | Select direction |
| G3 Content | Page copy, evidence register, claims, metadata, image selections | Content and Compliance Reviewers | Approve for build |
| G4 Core build | Interactive local site covering priority pages and breakpoints | Product Owner | Accept features or return defects |
| G5 Release candidate | Full QA evidence, deployment runbook, rollback plan | Executive Sponsor and IT Manager | Authorize deployment |
| G6 Production | Live smoke-test evidence and unresolved-issue list | Product Owner and IT Manager | Accept release |

# 10 Quality Management

| Quality area | Required checks |
| --- | --- |
| Content | Source alignment, spelling, dates, legal name, contact data, claims, attribution, CTA consistency, no placeholder text. |
| Responsive design | Representative widths, orientation changes, navigation, image crops, tables, cards, forms, typography, no overlap or overflow. |
| Accessibility | Landmarks, heading order, keyboard path, visible focus, contrast, labels, errors, alt text, link purpose, reduced motion, PDF accessibility review. |
| Performance | Image weight, caching, font loading, script inventory, layout shift, largest contentful paint, interaction latency. |
| Compatibility | Current Chrome, Edge, Firefox, Safari, iOS Safari, and Android Chrome where practical. |
| SEO | Unique titles and descriptions, one H1, canonicals, indexability, redirects, sitemap, robots, structured data, social metadata. |
| Forms and analytics | Validation, delivery, spam control, consent, privacy link, success state, error state, download events, form events. |
| Security and operations | Dependency and build review, secret exclusion, static host configuration, domain and SSL ownership, backups of the current site, restoration check, and release logging. |

# 11 Risk Management

| Risk | Probability / impact | Mitigation | Owner |
| --- | --- | --- | --- |
| Delayed approvals | Medium / High | Use fixed review windows, consolidated feedback, and explicit decision gates. | Product Owner |
| Unsupported public claims | High / High | Maintain claim register; remove or label content until evidence and permission are approved. | Compliance Reviewer |
| AI image misrepresentation | Medium / High | Use conceptual-only rules, asset register, human review, and clear labeling where appropriate. | Content Owner |
| Build and asset performance | Medium / Medium | Use static output, optimized WebP imagery, limited client JavaScript, performance budgets, and release checks. | Development Lead |
| Production access delay | Medium / Medium | Finish local release package; maintain access checklist and schedule IT handoff before release. | IT Manager |
| Static host route behavior | Medium / High | Test generated route folders, trailing slashes, redirects, PDF delivery, and cache behavior on the selected staging host before release. | Development Lead |
| Scope expansion | High / Medium | Apply change control with impact on schedule, cost, risk, and acceptance criteria. | Project Manager |
| Content ownership after launch | Medium / Medium | Provide editor guide, assign content owner, establish review calendar and governance. | Executive Sponsor |

# 12 Change Control

Every material change to scope, page structure, technology, approved content, claims, imagery, schedule, or acceptance criteria will be recorded before implementation. Small corrections within approved acceptance criteria do not require executive escalation but must still appear in the session log or change log.

## 12.1 Change Request Workflow

Record the request with identifier, date, requester, reason, affected pages, and desired outcome.

Assess impact on scope, schedule, quality, risk, content approval, technology, deployment, and existing completed work.

Recommend approve, defer, reject, or replace an existing backlog item.

Obtain the level of approval defined by the change authority matrix.

Update the plan, backlog, decision log, change log, status, and acceptance criteria before work starts.

Commit the governance update to the repository, then implement the approved change.

| Change class | Example | Authority |
| --- | --- | --- |
| Minor | Copy correction, spacing refinement, asset optimization within approved design | Product Owner |
| Moderate | New section, revised page flow, new image, new integration, schedule movement within one sprint | Product Owner plus Project Manager |
| Major | New page family, technology change, new legal claim, significant schedule or deployment change | Executive Sponsor |
| Emergency | Production defect, security exposure, broken form, critical public misinformation | IT Manager and Executive Sponsor; document immediately after containment |

# 13 Repository and Session Continuity

## 13.1 Repository Structure

The project repository will contain custom code, project documentation, approved content sources or references, design tokens, asset records, tests, deployment instructions, and current status. Sensitive production credentials, passwords, private keys, database exports, and unredacted personal information will never be committed.

| Path | Purpose |
| --- | --- |
| README.md | Project purpose, setup, operating rules, and links to current status. |
| STATUS.md | Single current-state summary: phase, sprint, completed work, work in progress, blockers, next actions, and restart instructions. |
| CHANGELOG.md | Chronological record of material project changes. |
| docs/plan/ | Approved plan and controlled revisions. |
| docs/decisions/ | Architecture and business decision records. |
| docs/requirements/ | Scope, page requirements, acceptance criteria, claims and evidence records. |
| docs/design/ | Design tokens, components, wireframes, approvals, and image direction. |
| docs/qa/ | Test plans, test results, accessibility, performance, and release evidence. |
| docs/deployment/ | Environment checklist, deployment runbook, rollback, and handoff. |
| assets/ai-register/ | Prompt summaries, asset IDs, approvals, alt text, rights and usage records; optimized public assets may live with the theme. |
| next-app/ | Selected Next.js and TypeScript static-export application, MDX Insights content, tests, assets, and deployment-safe configuration examples. |
| backlog/ | Prioritized backlog, sprint goals, and accepted work history. |
| prototype/ and wordpress/ | Preserved reference prototype and historical WordPress scaffold; not altered as part of the new review build. |

## 13.2 Mandatory End of Session Protocol

Review the user’s latest instructions and confirm whether scope, priority, or decisions changed.

Update STATUS.md with completed work, current state, blockers, unresolved questions, and the exact first action for the next session.

Update the backlog, change log, decision records, risk register, and plan when their underlying facts changed.

Record validation performed, including pages, devices, tests, files, or screenshots reviewed.

Run relevant checks and ensure no credentials, temporary exports, or private data are staged.

Keep repository changes and current status documented at the end of each session. Commit and push only when explicitly authorized for that release.

Report the commit identifier, deliverables, outstanding decisions, and next-session starting point to the user.

## 13.3 Start of Session Protocol

Read README.md, STATUS.md, the latest change-log entry, open decisions, and the active sprint backlog.

Check repository status and confirm the expected branch and last commit.

Verify that any new user instruction does not conflict with approved decisions or completed work.

Resume from the first action listed in STATUS.md unless the user reprioritizes the work.

# 14 Communication and Reporting

| Cadence | Audience | Content |
| --- | --- | --- |
| During active work | User / Product Owner | Concise progress updates, discoveries, decisions needed, and any material risk. |
| End of each session | User / Product Owner | Completed work, verification, commit, decisions, blockers, and next-session start. |
| Sprint review | Executive Sponsor and stakeholders | Working increment, acceptance results, planned next sprint, risks and changes. |
| Decision request | Named approver | Decision, recommendation, alternatives, consequences, and deadline. |
| Release readiness | Executive Sponsor and IT Manager | Scope delivered, defects, test evidence, deployment steps, rollback, and launch recommendation. |

# 15 Deployment and Handover

## 15.1 Production Preconditions

Final executive authorization and accepted release candidate.

Hosting and deployment access supplied through an approved secure method only after a production platform is selected and release is explicitly authorized; credentials are never stored in the repository.

Complete files and database backup with verified restore path.

Target hosting build support, domain and DNS controls, forms/email, scheduling, analytics, SSL, caching, privacy, and security constraints documented and approved.

Redirects, SEO metadata, analytics, forms, cookies, privacy language, and downloadable documents approved.

Maintenance window, responsible personnel, rollback threshold, and communication path confirmed.

## 15.2 Deployment Sequence

Freeze approved content and record the release commit and package checksum.

Back up production files and database.

Deploy the statically exported files to a staging or test destination after IT selects and approves the target host.

Verify static route behavior, redirects, metadata, assets, and the capability PDF against the approved site map.

Clear or invalidate the selected host's cache where applicable, then perform a production smoke test after separately authorized release.

Verify route responses, forms and email behavior, downloads, analytics if approved, robots, sitemap, SSL, responsive layouts, and search metadata.

Resolve launch-blocking issues or execute rollback.

Record production results, final status, known issues, ownership, and stabilization actions.

## 15.3 Handover Package

Accepted application source and deployment configuration for the production platform selected at a later approval gate.

Reusable page components, content authoring guidance, and verified deployment documentation.

Approved image library with asset and AI-generation register.

Content source of truth, page inventory, redirects, metadata, and claim register.

Editor guide, technical README, deployment runbook, rollback plan, and maintenance recommendations.

Test results, release notes, known issues, repository history, and final acceptance record.

# 16 Governance Artifacts

| Artifact | Owner | Update trigger |
| --- | --- | --- |
| Project Management Plan | Project Manager | Approved material change to scope, technology, schedule, governance, quality, or deployment |
| Product Backlog | Product Owner | New requirement, reprioritization, acceptance result, or change approval |
| STATUS.md | Delivery Lead | End of every working session and after any material blocker |
| Decision Log | Decision owner | Architecture, business, content, design, compliance, or release decision |
| Change Log | Project Manager | Every approved material change |
| Risk Register | Project Manager | New risk, changed exposure, mitigation action, or closure |
| Claim and Evidence Register | Compliance Reviewer | Any metric, client, logo, testimonial, outcome, credential, or past-performance change |
| AI Asset Register | Design and Content Owners | Each generated, revised, approved, rejected, or published AI image |
| QA Evidence | Quality Reviewer | Every test cycle and release candidate |
| Deployment Record | IT Manager | Every staging or production release |

# 17 Assumptions and Dependencies

The final Company Profile and Capability Statement remain the principal approved content sources.

PUL will identify a Product Owner able to consolidate feedback and accept work.

Executives and reviewers will normally respond within one to two business days.

Existing logo files, approved color values, photos, project evidence, and leadership information will be supplied where available.

The current WordPress/one.com website remains live and unchanged. The new Next.js application is a separate review build; production hosting and migration are undecided and require IT review and explicit approval.

Production access will be provided only when local work is approved for deployment.

Any legal, privacy, certification, or procurement statement requiring specialist review will be approved by an appropriate owner before publication.

# 18 Plan Maintenance and Version Control

This document is a controlled project artifact. The current approved version will be stored in the repository and in the PUL Global Partners website-planning folder. When a material project change is approved, the project manager will update the affected sections, increment the version, add a revision-history entry, update related repository artifacts, and commit the change before dependent work proceeds.

| Version | Date | Summary | Status |
| --- | --- | --- | --- |
| 1.0 | 16 September 2026 | Initial comprehensive plan for executive review | Superseded by 1.1 |
| 1.1 | 30 September 2026 | Approved architecture amendment: separate Next.js/TypeScript review build, MDX Insights, no initial CMS/database, production unchanged | Approved for local review build |

# 19 Approval Record

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Executive Sponsor |  | Approve / Revise / Hold |  |
| Product Owner |  | Approve / Revise / Hold |  |
| IT Manager |  | Acknowledge architecture and deployment responsibilities |  |
| Content and Compliance Reviewer |  | Acknowledge content and evidence responsibilities |  |

No design or development work will begin until PUL Global Partners explicitly authorizes implementation. Planning artifacts and repository governance may be refined during review without implying approval to build or deploy.